## Sheet1
QUERY LIST
Item | Date |  | Date | Response
(This is a continuous list. For date of issue refer to item date)
UNIVERSITY OF FORT HARE - FINANCE OFFICE CONVERSION
| For date of submission see email date |  | Kindly insert your response into this list
1 | 11-12-2025 | STRUCT ENG: Confirm surface bed thickness - structural drawings show layout but thickness not clearly indicated. Assume 100mm or 150mm?
2 | 11-12-2025 | STRUCT ENG: Confirm extent of new surface beds - Only where timber floors removed (45 m²) OR over all existing concrete areas (380 m²)? Cost impact ~R100,000
3 | 11-12-2025 | STRUCT ENG: Provide complete reinforcement schedules - Bar marks shown on Foundation Layout S-01-001 but schedules not provided
4 | 11-12-2025 | STRUCT ENG: Extract foundation dimensions from Foundation Layout S-01-001 Rev E for accurate quantity calculations
5 | 11-12-2025 | STRUCT ENG: Ring beam details and dimensions from Ring Beam Layout S-01-003 Rev E - Not currently measured in Foundations BOQ
6 | 11-12-2025 | STRUCT ENG/ARCH: Existing concrete floor condition survey required - Can floors be prepared and tiled directly or do new surface beds need to be cast over?
7 | 11-12-2025 | ARCH: Confirm screed extent - Notes say 'screeds where required'. All areas (380 m²) or selective areas only? Which areas can tiles go directly on prepared surface beds?
8 | 11-12-2025 | ARCH: Confirm screed thickness - 50mm throughout or varies by location? Ablutions confirmed 50mm to falls.
9 | 11-12-2025 | STRUCT ENG: Confirm DPC specification under surface beds - Type, thickness, and product specification required
10 | 11-12-2025 | STRUCT ENG/ARCH: Services coordination critical - All electrical conduits, plumbing pipes and drainage must be in place BEFORE surface bed casting. Services drawings required urgently.
11 | 08-12-2025 | ARCH/CIVIL ENG: External paving extent? Will this form part of the Architectural contract or separate civil contract?
12 | 08-12-2025 | CIVIL ENG: Paving Layerworks drawing 2025-12-10 received. Confirm base course depths, paver thickness and exact paving area
13 | 08-12-2025 | ELEC ENG: Electrical Installation Bills of Quantities required - Demolitions, new installation, lighting, power, data
14 | 08-12-2025 | MECH ENG: Mechanical Installation Bills of Quantities required - HVAC, ventilation, fire systems
15 | 08-12-2025 | CIVIL ENG: Civil engineering drawings required - Drainage, stormwater, external works details
16 | 08-12-2025 | STRUCT ENG: Structural Engineering drawings required | 10-12-2025 | Received - S-01 series
17 | 08-12-2025 | H&S AGENT: Health and Safety Specification and Bill of Quantities required
18 | 08-12-2025 | ARCH: Glass thickness to windows, shopfronts and doors - Specification required for pricing
19 | 08-12-2025 | ARCH: Wall and floor tiling specs? I.e. at this stage is the architect wanting the QS to price for Porcelain tiles or Ceramic tiles?
20 | 10-12-2025 | ARCH: Are photos of the existing building available for tenderers to review with the tender documents?
21 | 10-12-2025 | STRUCT ENG: Where one brick and cavity walls are to be demolished - Confirm which internal walls are loadbearing for structural demolition methodology
22 | 10-12-2025 | STRUCT ENG/ARCH: Please confirm which external walls are cavity construction vs solid - Required for accurate brickwork quantities | 10-12-2025 | Structural drawings issued
23 | 10-12-2025 | ARCH: Exact built-in cupboard linear metres and dimensions - Site measurement required or provide detailed joinery drawings
24 | 10-12-2025 | ARCH: Confirmation of existing window and door counts vs drawings - Physical site count recommended
25 | 10-12-2025 | ARCH: Tile colour and exact product specification - Client selection required before final pricing
26 | 10-12-2025 | ARCH: Skirting colour selection - Capco Gamma products, colours to be confirmed
27 | 10-12-2025 | ARCH: Paint colours for all areas - Colour schedule required
28 | 11-12-2025 | SURVEYOR: Site survey required for existing floor levels and variations - Critical for accurate surface bed/screed thickness calculations
29 | 11-12-2025 | GEOTECH: Existing ground conditions for external works - Geotechnical report or trial pits recommended for paving sub-base design
30 | 10-12-2025 | CONTRACTOR: Access for plant and materials delivery - Site visit required to assess access constraints
|  | CIVIL ENG: Soil Tests | 11-12-2025 | Allow R25 000.00 for soil tests to be carried out by the contractor