## Sheet1
|  | QUERY LIST | RESPONSE
Item | Date |  | Date | #VALUE!
(This is a continuous list. For date of issue refer to email date)
UNIVERSITY OF FORT HARE - FINANCE OFFICE CONVERSION
| For date of submission see email date |  | Kindly insert your response into this list
1 | 08-12-2025 | ARCH/CIVIL ENG: External paving extent? Will this be replaced? | 11-142-2025 | See previous response sent
2 | 08-12-2025 | ELEC ENG: Electrical Installation Bills of Quantities required
3 | 08-12-2025 | MECH ENG: Mechanical Installation Bills of Quantities required - HVAC, ventilation, fire systems | 10-12-2025 | Received Bills for HVAC airconditioning and ventilation. Fire Systems allowed as a Prov Sum
4 | 08-12-2025 | CIVIL ENG: Civil engineering drawings required - Pls see items below. Work to existing paving? Work to existing water and drain piping incl blanking off? | 10-12-2025 | CIVIL ENG: says civil drawings may not be needed. QS: see quenstions re plumbing, drainage, suface beds and paving below
5 | 08-12-2025 | STRUCT ENG: Structural Engineering drawings required | 10-12-2025 | Received - S-01 series
6 | 08-12-2025 | H&S AGENT: Health and Safety Specification and Bills of Quantities required
7 | 08-12-2025 | ARCH: Glass thickness to windows, shopfronts and doors? |  | See previous response sent on glass thickness - we cannot specify that.
8 | 08-12-2025 | ARCH: Wall and floor tiling specs? I.e. at this stage only type (porcelain, cermic, etc) and thickness required
9 | 10-12-2025 | ARCH: Are photos of the existing building available?
10 | 10-12-2025 | STRUCT ENG: Where one brick and cavity walls are to be demolished, what is required for support of roof structure? Which internal walls are loadbearing?
11 | 10-12-2025 | STRUCT ENG/ARCH: Please confirm which external walls are cavity construction versus solid brickwork? Refer Dwngs A-01-1002, A-11-1000 | 10-12-2025 | Structural dwngs issued
12 | 10-12-2025 | ARCH: Garage door spec and dimensions, number of doors (2?) required?
13 | 10-12-2025 | ARCH: Facade doors - specific locations and quantities unclear. How many? Sizes? Separate from door count?
14 | 10-12-2025 | ARCH: Areas where timber flooring to be removed dimensions? Please identify areas, thickness of flooring and battens, is underfloor structure retained?
15 | 10-12-2025 | ARCH: Floor tile removal areas dimensions? Please show areas, thickness of tiles and screed, type of tiles?
16 | 10-12-2025 | CIVIL ENG/ARCH: Paving demolition areas not dimensioned or clearly defined. Exact area, type of paving (concrete/pavers/asphalt?), thickness/depth?
17 | 10-12-2025 | ARCH: Steps and nib wall dimensions not provided. Dimensions of steps (width, length, risers), nib wall dimensions and height, material?
18 | 10-12-2025 | ARCH: Is fence included in scope? Height of brick portion versus fence portion not indicated
19 | 10-12-2025 | ARCH: Roof areas difficult to scale accurately from plan. Please confirm roof areas. Are the measurements shown taken on plan or on slope? Roof pitch?
20 | 10-12-2025 | ARCH: Are all ceilings demolished or specific areas? Type of ceiling to be removed?
21 | 11-12-2025 | CIVIL ENG/ARCH: Which drainage/water lines retained? Termination requirements and details (capped, plugged)?
22 | 11-12-2025 | ELEC ENG: No mention of electrical removal in demolition notes. Refer Dwng A-01-1002. Are electrical fittings, switches, sockets removed? DB boards? Conduits/cables? How much builder's work required in making good?
23 | 11-12-2025 | ARCH: Site Plan required. No indication of access routes or site establishment. Where can contractor establish site? Access route? Working hour restrictions? Protection to residences?
24 | 11-12-2025 | ARCH: Existing ablution block to remain - location not clearly marked. Exact location, protection required? Services running through?
25 | 11-12-2025 | ARCH: Finishing Schedule required. Items require "make good to match existing" but existing finishes not specified (timber type, plaster, paint)?
26 | 11-12-2025 | STRUCT ENG: Wall stability during demolition - no structural details. Refer Dwng A-01-1002. Which wall needs temporary support? Method required (props, needling)?
27 | 11-12-2025 | STRUCT ENG: Is it necessary to describe the demolition sequence?
28 | 11-12-2025 | ARCH: Instruction - Finish to concrete beam to be "Degree of Accuracy - Class 1" |  | Noted
29 | 11-12-2025 | STRUCT ENG: Confirm surface bed thickness - structural drawings show layout but thickness not clearly indicated. Assume 100mm or 150mm?
30 | 11-12-2025 | STRUCT ENG: Pls confirm extent of new surface beds - Only where timber floors removed OR over all existing concrete areas. Cost impact ~R100,000
31 | 11-12-2025 | STRUCT ENG: Reinforcement Schedules required. In their absence what kg/m3 proportions should we measure? Bar marks shown on Foundation Layout S-01-001 but schedules not provided
32 | 11-12-2025 | STRUCT ENG/ARCH: Existing concrete floor condition survey required - Can floors be prepared and tiled directly or do new surface beds need to be cast over?
33 | 11-12-2025 | ARCH: Confirm screed extent - Notes say 'screeds where required'. All areas (380 m²) or selective areas only? Which areas can tiles go directly on prepared surface beds?
34 | 11-12-2025 | ARCH: Confirm screed thickness - 50mm throughout or varies by location? Ablutions confirmed 50mm to falls.
35 | 11-12-2025 | ELEC ENG/MECH ENG/CIVIL ENG/STRUCT ENG/ARCH: Concrete encasing or other builder's work to services beneath floors required. Coordination required. Electrical conduits, plumbing pipes and drainage must be in place before surface beds are cast. Services drawings required
36 | 08-12-2025 | CIVIL ENG: Please clarify extent of and specs for taking up and laying new paving.
37 | 08-12-2025 | ELEC ENG: Electrical Installation Bills of Quantities required - Demolitions, new installation, lighting, power, data
38 | 08-12-2025 | CIVIL ENG: Civil engineering drawings required - Drainage, stormwater, external works details
39 | 08-12-2025 | H&S AGENT: Health and Safety Specification and Bill of Quantities required | 10-12-2025 | Received - Spec and Bills
40 | 10-12-2025 | STRUCT ENG/ARCH: Please confirm which external walls are cavity construction vs solid - Required for accurate brickwork quantities | 10-12-2025 | Structural drawings issued
41 | 10-12-2025 | ARCH: Built-in cupboards approximate dimensions required to allow a Provisional Sum. Will cupboard details follow after tender?
42 | 11-12-2025 | ARCH: Should an item be included for the contractor to engage a Land Surveyor to survey the existing floor levels and variations? This may be needed to confirm surface bed levels and screed thicknesses
43 | 11-12-2025 | GEOTECH: Existing ground conditions for external works - Geotechnical report or trial pits recommended for paving sub-base design | 11-12-2025 | CIVIL ENG: Allow a Prov Sum of R25 000.00 for test pits.