## Queries List
UNIVERSITY OF FORT HARE
FINANCE OFFICE CONVERSION - ALICE CAMPUS
QUERIES LIST - DEMOLITIONS AND ALTERATIONS
Drawings Referenced: A-01-1002, A-01-1003, A-12-2000, A-11-1000
Query No. | Issue/Question | Current Assumption | Information Required | Drawing Ref | Priority | Response
1.1 | Exact number and size of veranda columns to be demolished not clearly shown | 4 columns @ 230mm x 230mm | Exact number, dimensions (width x depth), height. Any columns to be retained? | A-01-1002 | Low
1.2 | Cannot confirm which external walls are cavity construction versus solid brickwork | Garage walls: Cavity (280-330mm) Boundary: One brick (230mm) | Confirm wall construction type for garage walls, boundary wall thickness | A-01-1002, A-11-1000 | High
1.3 | Cannot determine which internal walls are loadbearing | All internal walls = 110mm non-loadbearing | Which internal walls are loadbearing (230mm)? Structural engineer confirmation required | Structural dwgs req | High
2.1 | Exact run length and depth of built-in cupboards not dimensioned | 15 linear metres total | Exact linear metres, depth of cupboards, height to top of concrete soffit | A-01-1002 | High
2.2 | Built-in joinery with open shelving - dimensions not provided | Included as 1 item | Dimensions of joinery unit. Is this separate from BICs or part of them? | A-01-1002 | Low
3.1 | Individual window dimensions not marked on all windows | 12 windows total (estimated) | Exact count of windows, individual sizes, which have ironmongery/burglar bars? | A-01-1002, elevations | Medium
3.2 | Garage door dimensions not provided | Estimate 5.0m x 2.1m opening | Exact garage door dimensions, number of doors (2?), type of doors | A-01-1002 | Medium
3.3 | Facade doors - specific locations and quantities unclear | Included in 10 doors total | How many facade doors? Sizes? Separate from door count? | A-01-1002 | Medium
4.1 | Areas where timber flooring to be removed not dimensioned | 45 m² of timber flooring | Exact areas, thickness of flooring and battens, is underfloor structure retained? | A-01-1002 | Medium
4.2 | Floor tile removal areas not clearly dimensioned | 25 m² of floor tiles | Exact areas, thickness of tiles and screed, type of tiles? | A-01-1002 | Medium
5.1 | Paving demolition areas not dimensioned or clearly defined | 80 m² of paving | Exact area, type of paving (concrete/pavers/asphalt?), thickness/depth | A-01-1002 | High
5.2 | Steps and nib wall dimensions not provided | Included as 1 item | Dimensions of steps (width, length, risers), nib wall dimensions and height, material? | A-01-1002 | Low
5.3 | Height of brick portion versus fence portion not indicated | 2.38m brick height assumed | Exact height of brickwork, fence height above, is fence included in scope? | A-01-1002, sections | Medium
6.1 | Roof areas difficult to scale accurately from plan | Garage: 55m², Main: 280m², Veranda: 35m² | Confirm exact roof areas. Measurements on plan or on slope? Roof pitch? | A-01-1003 | High
6.2 | Extent of ceiling demolition not clearly indicated | All ceilings under demolished roof | Are all ceilings demolished or specific areas? Type of ceiling? Height? | A-01-1003, A-12-2000 | Medium
7.1 | Plumbing to be "blanked off" or "retained" - extent not detailed | Allowance in descriptions | Which drainage/water lines retained? Termination requirements (capped, plugged)? | A-01-1002, services | Medium
7.2 | No mention of electrical removal in demolition notes | Not included in scope | Are electrical fittings, switches, sockets removed? DB boards? Conduits/cables? | Electrical dwgs req | High
8.1 | Existing ablution block to remain - location not clearly marked |  | Exact location, protection required? Services running through? | A-01-1002 | Low
8.2 | Shrubs, washing lines, external waste extent not defined | Included as 1 item | Number/size of shrubs, washing line locations, what is "external waste"? Disposal? | A-01-1002 | Low
8.3 | No indication of access routes or site establishment |  | Where can contractor establish site? Access route? Working hour restrictions? Protection to residences? | Site plan required | Low
9.1 | Items require "make good to match existing" but finishes not specified |  | Specification of existing finishes (timber type, plaster, paint). Samples available? | Finishes schedule req | Low
9.2 | Wall stability during demolition - no structural details |  | Which wall needs temporary support? Method required (props, needling)? Structural engineer input | A-01-1002, structural | Medium
PRIORITY LEGEND:
High | Affects pricing significantly
Medium | Affects methodology or quantities
Low | Can estimate or assume
SUMMARY BY PRIORITY:
High Priority: | 6 queries (Queries 1.2, 1.3, 2.1, 5.1, 6.1, 7.2)
Medium Priority: | 9 queries (Queries 3.1-3.3, 4.1-4.2, 5.3, 6.2, 7.1, 9.2)
Low Priority: | 6 queries (Queries 1.1, 2.2, 5.2, 8.1-8.3, 9.1)
ACTIONS REQUIRED:
Architect: | Confirm dimensions, provide finishes schedule, clarify scope items
Structural Engineer: | Identify loadbearing walls, temporary support requirements, demolition sequence
Services Engineers: | Electrical demolition scope, plumbing/drainage termination details
Site Visit Required: | Verify conditions, confirm wall types, measure areas, photograph finishes
Please respond to queries by: | [Insert date]