## Sheet1
|  | QUERY LIST | RESPONSE
Item | Date |  | Date | #VALUE!
(This is a continuous list. For date of issue refer to email date)
UNIVERSITY OF FORT HARE - FINANCE OFFICE CONVERSION
| For date of submission see email date |  | Kindly insert your response into this list
1 | 08-12-2025 | ARCH: External paving extent? Will this be replaced?
2 | 08-12-2025 | ELEC ENG: Electrical Installation Bills of Quantities required
3 | 08-12-2025 | MECH ENG: Mechanical Installation Bills of Quantities required
4 | 08-12-2025 | CIVIL ENG: Civil engineering drawings required
5 | 08-12-2025 | STRUCT ENG: Structural Engineering drawings required
6 | 08-12-2025 | H&S AGENT: Health and Safety Specification and Bills of Quantities required
7 | 08-12-2025 | ARCH: Glass thickness to windows, shopfronts and doors?
8 | 08-12-2025 | ARCH: Wall and floor tiling specs? I.e. at this stage only type (porcelain, cermic, etc) and thickness required
9 | 10-12-2025 | ARCH: Are photos of the existing building available?
10 | 10-12-2025 | STRUCT ENG: Where one brick and cavity walls are to be demolished, what is required for support of roof structure? Which internal walls are loadbearing?
11 | 10-12-2025 | STRUCT ENG/ARCH: Please confirm which external walls are cavity construction versus solid brickwork? Refer Dwngs A-01-1002, A-11-1000
12 | 10-12-2025 | ARCH: Garage door spec and dimensions, number of doors (2?) required?
13 | 10-12-2025 | ARCH: Facade doors - specific locations and quantities unclear. How many? Sizes? Separate from door count?
14 | 10-12-2025 | ARCH: Areas where timber flooring to be removed dimensions? Please identify areas, thickness of flooring and battens, is underfloor structure retained?
15 | 10-12-2025 | ARCH: Floor tile removal areas dimensions? Please show areas, thickness of tiles and screed, type of tiles?
16 | 10-12-2025 | ARCH: Paving demolition areas not dimensioned or clearly defined. Exact area, type of paving (concrete/pavers/asphalt?), thickness/depth?
17 | 10-12-2025 | ARCH: Steps and nib wall dimensions not provided. Dimensions of steps (width, length, risers), nib wall dimensions and height, material?
18 | 10-12-2025 | ARCH: Is fence included in scope? Height of brick portion versus fence portion not indicated
19 | 10-12-2025 | ARCH: Roof areas difficult to scale accurately from plan. Please confirm roof areas. Are the measurements shown taken on plan or on slope? Roof pitch?
20 | 10-12-2025 | ARCH: Are all ceilings demolished or specific areas? Type of ceiling?
21 | 11-12-2025 | CIVIL ENG/ARCH: Which drainage/water lines retained? Termination requirements and details (capped, plugged)?
22 | 11-12-2025 | ELEC ENG: No mention of electrical removal in demolition notes. Refer Dwng A-01-1002. Are electrical fittings, switches, sockets removed? DB boards? Conduits/cables? How much builder's work required in making good?
23 | 11-12-2025 | ARCH: Site Plan required. No indication of access routes or site establishment. Where can contractor establish site? Access route? Working hour restrictions? Protection to residences?
24 | 11-12-2025 | ARCH: Existing ablution block to remain - location not clearly marked. Exact location, protection required? Services running through?
25 | 11-12-2025 | ARCH: Finishing Schedule required. Items require "make good to match existing" but existing finishes not specified (timber type, plaster, paint)?
26 | 11-12-2025 | STRUCT ENG: Wall stability during demolition - no structural details. Refer Dwng A-01-1002. Which wall needs temporary support? Method required (props, needling)?
27 | 11-12-2025 | STRUCT ENG: Is it necessary to describe the demolition sequence?