# UFHARE PROJECT STATUS

## University of Fort Hare - Conversion of Old Clinic to Finance Department Offices

Last Updated: 2026-01-04

Project Stage: Pre-Tender

BOQ Target: Draft for client review

Measurement Standard: ASAQS SSM7 (2015) / DQRules v2.0

__________________________________________________

## 1. PROJECT OVERVIEW

### 1.1 Project Description

Conversion of an existing old clinic building into Finance Department Offices at the University of Fort Hare Alice Campus.

### 1.2 Scope Summary

Building Type: Office conversion (existing clinic)

Location: Alice Campus, University of Fort Hare, Eastern Cape

Work Includes:

Demolition of existing internal elements

New foundations and structural elements (ring beams, surface beds)

Internal walls and partitions

Complete finishes (walls, floors, ceilings)

Fenestration (doors, windows, shopfronts, gates)

Fixed furniture (security desk, kitchenette)

New external paving

Full MEP installations (Electrical, HVAC, Fire Protection)

Landscaping (R100k PC Sum)

### 1.3 Key Dates

| Milestone | Date |
| --- | --- |
| Drawings received | 2025-11-05 |
| Query List Rev 1 issued | 2025-12-08 |
| SVA Query responses | 2025-12-09 |
| Query List Rev 2 issued | 2025-12-11 |
| Draft BOQ target | 2025-12-17 |

__________________________________________________

## 2. CONSULTANT TEAM

| Role | Company | Contact | Email |
| --- | --- | --- | --- |
| Client | University of Fort Hare | Bubele Dyantyi (Project Manager) | sbdyantyi@ufh.ac.za |
| Client Rep | University of Fort Hare | Nqabisa Bala | nbala@ufh.ac.za |
| Architect | SVA International (Pty) Ltd | Tony Danev | tony@svarchitects.com |
| QS (Lead) | Excel Quantity Surveyors | Mawande Songo | mawande@excelqs.co.za |
| QS (Senior) | Dell QS / Excel QS | Ron Dell | ron@excelqs.co.za |
| Structural | Bara Consult | Alex Semple | alex@baraconsult.com |
| MEP | Cadutoitec | Andries Strauss | andries@cadutoitec.co.za |
| MEP | Cadutoitec | Ashraf Brown | ashraf@cadutoitec.co.za |
| MEP | Cadutoitec | Petrus Strydom | petrus@cadutoitec.co.za |
| H&S | Safe Practice | Jay Bhana | buffalo@safepractice.co.za |
| H&S | Safe Practice | Stiaan Burger | - |

__________________________________________________

## 3. DOCUMENT INVENTORY

Base Path: Projects\UFHARE\1 Pre-Tender\

### 3.1 Architectural Drawings (57 files)

#### Floor Plans

| Drawing No. | Title | Rev | File | Split File |
| --- | --- | --- | --- | --- |
| A-(11)1000 | Ground Storey Plan | 4 | Architectural Drawings\A-(11)1000-Ground Storey Plan-(4).pdf | split_pdfs\A-(11)1000-Ground Storey Plan-(4)\A-(11)1000-Ground Storey Plan-(4)_page_001.png |
| A-(11)1001 | Roof Plan | 4 | Architectural Drawings\A-(11)1001-Roof Plan-(4).pdf | split_pdfs\A-(11)1001-Roof Plan-(4)\A-(11)1001-Roof Plan-(4)_page_001.png |
| A-(11)1002 | Clerestory Plan Level | 3 | Architectural Drawings\A-(11)1002-Clerestory Plan Level-(3).pdf | - |
| A-(11)1003 | General Arrangement Layout | 4 | Architectural Drawings\A-(11)1003-General Arrangement Layout-(4).pdf | split_pdfs\A-(11)1003-General Arrangement Layout-(4)\A-(11)1003-General Arrangement Layout-(4)_page_001.png |

#### Demolition

| Drawing No. | Title | Rev | File | Split File |
| --- | --- | --- | --- | --- |
| A-(01)1002 | Demolition Plan | 3 | Architectural Drawings\A-(01)1002-Demolition Plan(3).pdf | split_pdfs\A-(01)1002-Demolition Plan(3)\A-(01)1002-Demolition Plan(3)_page_001.png |
| A-(01)1003 | Demolition Plan | 2 | Architectural Drawings\A-(01)1003-DEMOLITION PLAN-(2).pdf | - |

#### Sections & Elevations

| Drawing No. | Title | Rev | File | Split File |
| --- | --- | --- | --- | --- |
| A-(12)2000 | Sections | 4 | Architectural Drawings\A-(12)2000-Sections-(4).pdf | split_pdfs\A-(12)2000-Sections-(4)\A-(12)2000-Sections-(4)_page_001.png |
| A-(13)3000 | Elevations | 4 | Architectural Drawings\A-(13)3000-Elevations-(4).pdf | split_pdfs\A-(13)3000-Elevations-(4)\A-(13)3000-Elevations-(4)_page_001.png |

#### Ceiling Plans

| Drawing No. | Title | Rev | File | Split File |
| --- | --- | --- | --- | --- |
| A-(14)1000 | Ceiling Plan | 3 | Architectural Drawings\A-(14)1000-Ceiling Plan-(3).pdf | split_pdfs\A-(14)1000-Ceiling Plan-(3)\A-(14)1000-Ceiling Plan-(3)_page_001.png |
| A-(14)1003 | Ground Storey Ceiling Plan | 1 | Architectural Drawings\A-(14)1003-GROUND STOREY CEILING PLAN (1).pdf | split_pdfs\A-(14)1003-GROUND STOREY CEILING PLAN (1)\A-(14)1003-GROUND STOREY CEILING PLAN (1)_page_001.png |

#### Fenestration Key Plans

| Drawing No. | Title | Rev | File |
| --- | --- | --- | --- |
| A-(30)1001 | Fenestration Key Plan | 2 | Architectural Drawings\A-(30)1001-Fenestration Key Plan-(2).pdf |
| A-(30)1002 | Fenestration Key Plan - Clerestory | 2 | Architectural Drawings\A-(30)1002-Fenestration Key Plan_Clerestory-(2).pdf |

#### Doors (8 types + 2 gates)

| Drawing No. | Title | Rev |
| --- | --- | --- |
| A-(31)5001 | Door D01 | 1 |
| A-(31)5002 | Door D02 | 1 |
| A-(31)5003 | Door D03 | 1 |
| A-(31)5004 | Door D04 | 1 |
| A-(31)5005 | Door D05 | 1 |
| A-(31)5006 | Door D06 | 1 |
| A-(31)5007 | Gate G01 | 1 |
| A-(31)5008 | Door D07 | 1 |
| A-(31)5009 | Door D08 | 1 |
| A-(31)5010 | Gate G02 | 1 |

#### Shopfronts (9 types)

| Drawing No. | Title | Rev |
| --- | --- | --- |
| A-(32)5001 | Shopfront SF01 | 1 |
| A-(32)5002 | Shopfront SF02 | 1 |
| A-(32)5003 | Shopfront SF03 | 1 |
| A-(32)5004 | Shopfront SF04 | 1 |
| A-(32)5005 | Shopfront SF05 | 1 |
| A-(32)5006 | Shopfront SF06 | 1 |
| A-(32)5007 | Shopfront SF07 | 1 |
| A-(32)5008 | Shopfront SF08 | 1 |
| A-(32)5009 | Shopfront SF09 | 1 |

#### Windows (6 types)

| Drawing No. | Title | Rev |
| --- | --- | --- |
| A-(35)5001 | Window W01 | 1 |
| A-(35)5002 | Window W02 | 1 |
| A-(35)5003 | Window W03 | 1 |
| A-(35)5004 | Window W04 | 1 |
| A-(35)5005 | Window W05 | 1 |
| A-(35)5006 | Window W06 | 1 |

#### Finishes & Details

| Drawing No. | Title | Rev | File | Split File |
| --- | --- | --- | --- | --- |
| A-(50)6001 | Ablution Details | 1 | Architectural Drawings\A-(50)6001-Ablution Details-(1).pdf | split_pdfs\A-(50)6001-Ablution Details-(1)\A-(50)6001-Ablution Details-(1)_page_001.png |
| A-(51)1001 | Wall Finishes Layout | 1 | Architectural Drawings\A-(51)1001-Wall Finishes Layout(1).pdf | - |
| A-(52)1001 | Floor Finishes Layout | 1 | Architectural Drawings\A-(52)1001-Floor Finishes Layout(1).pdf | split_pdfs\A-(52)1001-Floor Finishes Layout(1)\A-(52)1001-Floor Finishes Layout(1)_page_001.png |
| A-(52)1002 | Skirtings | 1 | Architectural Drawings\A-(52)1002-Skirtings(1).pdf | split_pdfs\A-(52)1002-Skirtings(1)\A-(52)1002-Skirtings(1)_page_001.png |
| A-(53)2001 | Seating and Duct Detail | 1 | Architectural Drawings\A-(53)2001-Seating and Duct Detail-(1).pdf | split_pdfs\A-(53)2001-Seating and Duct Detail-(1)\A-(53)2001-Seating and Duct Detail-(1)_page_001.png |
| A-(53)2002 | Seating Detail | 1 | Architectural Drawings\A-(53)2002-Seating Detail-(1).pdf | - |
| A-(53)2003 | Concrete Canopy Detail | 1 | Architectural Drawings\A-(53)2003-Concrete Canopy Detail-(1).pdf | - |

#### Fixed Furniture & Joinery

| Drawing No. | Title | Rev | File | Split File |
| --- | --- | --- | --- | --- |
| A-(74)1001 | Fixed Furniture and Fittings Key Plan | 1 | Architectural Drawings\A-(74)1001-Fixed Furniture and Fittings Key Plan(1).pdf | split_pdfs\A-(74)1001-Fixed Furniture and Fittings Key Plan(1)\A-(74)1001-Fixed Furniture and Fittings Key Plan(1)_page_001.png |
| A-(74)6001 | JT01 - Security Desk | 1 | Architectural Drawings\A-(74)6001-JT01 - Security Desk(1).pdf | - |
| A-(74)6002 | JT02 - Kitchenette | 1 | Architectural Drawings\A-(74)6002-JT02 - Kitchenette(1).pdf | - |

#### External Works

| File | Description | Split File |
| --- | --- | --- |
| New Paving Layout.pdf | External paving layout | split_pdfs\New Paving Layout\New Paving Layout_page_001.png |

### 3.2 Structural Drawings (6 files)

Drawing Series: S-01-25055-20-XXX

| Drawing No. | Title | Rev | File | Split File |
| --- | --- | --- | --- | --- |
| S-01-25055-20-000 | Standard Notes | A | Structural Drawings\S-01-25055-20-000-Rev A-Standard Notes.pdf | - |
| S-01-25055-20-001 | Foundation Layout | E | Structural Drawings\S-01-25055-20-001-Rev E-Foundation Layout.pdf | split_pdfs\S-01-25055-20-001-Rev E-Foundation Layout\S-01-25055-20-001-Rev E-Foundation Layout_page_001.png |
| S-01-25055-20-001 | Foundation Layout (Marked) | E | Structural Drawings\S-01-25055-20-001-Rev E-Foundation Layout- Ron Marked.pdf | split_pdfs\S-01-25055-20-001-Rev E-Foundation Layout- Ron Marked\S-01-25055-20-001-Rev E-Foundation Layout- Ron Marked_page_001.png |
| S-01-25055-20-002 | Surface Bed Layout | E | Structural Drawings\S-01-25055-20-002-Rev E-Surface Bed Layout.pdf | split_pdfs\S-01-25055-20-002-Rev E-Surface Bed Layout\S-01-25055-20-002-Rev E-Surface Bed Layout_page_001.png |
| S-01-25055-20-003 | Ring Beam Layout | E | Structural Drawings\S-01-25055-20-003-Rev E-Ring Beam Layout.pdf | split_pdfs\S-01-25055-20-003-Rev E-Ring Beam Layout\S-01-25055-20-003-Rev E-Ring Beam Layout_page_001.png |
| S-01-25055-20-004 | Sections | D | Structural Drawings\S-01-25055-20-004-Rev D-Sections.pdf | split_pdfs\S-01-25055-20-004-Rev D-Sections\S-01-25055-20-004-Rev D-Sections_page_001.png |

### 3.3 Civil Drawings (1 file)

| File | Description |
| --- | --- |
| Civil Drawings\2025-12-10 Paving Layerworks.pdf | Paving layer specification |

### 3.4 MEP Packages

#### HVAC (Extracted)

| File | Description |
| --- | --- |
| Mechanical Installation\HVAC\HVAC_Extracted\P8080M02-BOQ_RevA.xlsx | HVAC BOQ |
| Mechanical Installation\HVAC\HVAC_Extracted\P8080M02-001_B - HVAC LAYOUT.pdf | HVAC Layout |
| Mechanical Installation\HVAC\HVAC_Extracted\P8080M02-Spec and BOQ_Rev A.pdf | HVAC Specification |

#### Fire Protection (Extracted)

| File | Description | Split File |
| --- | --- | --- |
| Mechanical Installation\Fire Protection\Fire_Extracted\P8080M07-BOQ.xlsx | Fire Protection BOQ | - |
| Mechanical Installation\Fire Protection\Fire_Extracted\P8080M07-001_A - FIRE AND WAYFINDING LAYOUT.pdf | Fire & Wayfinding Layout | split_pdfs\P8080M07-001_A - FIRE AND WAYFINDING LAYOUT\P8080M07-001_A - FIRE AND WAYFINDING LAYOUT_page_001.png |
| Mechanical Installation\Fire Protection\Fire_Extracted\P8080M07-Spec and BOQ.pdf | Fire Protection Specification | - |

#### Electrical (Extracted)

| File | Description | Split Files |
| --- | --- | --- |
| Electrical Installation\Elec_BOQ_Extracted\251212-UFH Alice Campus-Finance Offices - Elec BOQ Rev00.xlsx | Electrical BOQ | - |
| Electrical Installation\Elec_BOQ_Extracted\P8080E01-003 DB LAYOUT.pdf | Distribution Board Layout | - |
| Electrical Installation\Elec_BOQ_Extracted\P8099E01-001_C - POWER LAYOUT.pdf | Power Layout | split_pdfs\P8099E01-001_C - POWER LAYOUT\P8099E01-001_C - POWER LAYOUT_page_001.png |
| Electrical Installation\Elec_BOQ_Extracted\P8099E01-002_C - LIGHTINGLAYOUT.pdf | Lighting Layout | split_pdfs\P8099E01-002_C - LIGHTINGLAYOUT\P8099E01-002_C - LIGHTINGLAYOUT_page_001.png |
| Electrical Installation\Elec_BOQ_Extracted\UHF Alice Campus Finance Office - Electrical Spec Rev00 (251212-P8080).pdf | Electrical Specification (40pp) | split_pdfs\UHF Alice Campus Finance Office - Electrical Spec Rev00 (251212-P8080)\ (40 PNGs: _page_001.png to _page_040.png) |

#### Fire Detection (Extracted)

| File | Description | Split Files |
| --- | --- | --- |
| Electrical Installation\FD_BOQ_Extracted\251212-UFH Alice Campus-Finance Offices - FD BOQ Rev00 (Contractors).xlsx | Fire Detection BOQ | - |
| Electrical Installation\FD_BOQ_Extracted\P8080E06-001_00 - ICT Services.pdf | ICT Services Layout | - |
| Electrical Installation\FD_BOQ_Extracted\UFH Alice Campus Finance Office - Fire Detection Spec Rev00 (251212-P8080).pdf | Fire Detection Specification (42pp) | split_pdfs\UFH Alice Campus Finance Office - Fire Detection Spec Rev00 (251212-P8080)\ (42 PNGs: _page_001.png to _page_042.png) |

### 3.5 Health & Safety

| File | Description |
| --- | --- |
| Health and Safety Spec and BoQ\H and S Spec_Conversion Project 20251211.pdf | H&S Specification |
| Health and Safety Spec and BoQ\H and S -BOQ- Conversion Project 20250512.xlsx | H&S BOQ |

### 3.6 Query Lists & Responses

| File | Description | Date |
| --- | --- | --- |
| QUERY Lists\UFHare Conversion- QUERY LIST 20251211 Rev2.xlsx | Latest Query List | 2025-12-11 |
| QUERY Lists\UFHare Conversion- QUERY LIST 20251211 Rev2.pdf | PDF version | 2025-12-11 |
| QUERY Lists\Copy of UFHare Conversion- QUERY LIST 20251211 - SVA Comments.pdf | Architect responses | 2025-12-11 |
| QUERY Lists\Copy of UFHare QUERY LIST 20251208 - Comments SVA (003).pdf | Earlier responses | 2025-12-08 |

### 3.7 Measurement Files

#### Primary BOQ Documents

| File | Description | Status |
| --- | --- | --- |
| MEASUREMENT UFHare\Draft Excel Bills before Import WORKSHEETS\UFH_Complete_BOQ_with_Mechanical 20251211 1539.xlsx | Main consolidated BOQ | Latest |
| MEASUREMENT UFHare\Draft Excel Bills before Import WORKSHEETS\UFH_BOQ_QSPlus_Import_5.xlsx | QSPlus import format | Ready |
| MEASUREMENT UFHare\Draft Excel Bills before Import WORKSHEETS\UFH_BOQ_Conventional_Format.xlsx | Conventional format | Alternative |

#### Trade-Specific Measurements

| File | Trade | Status |
| --- | --- | --- |
| MEASUREMENT UFHare\Claude Measurements\UFH_Foundations_700mm Repaired - FInal USED.xlsx | Foundations | FINAL |
| MEASUREMENT UFHare\Draft Excel Bills before Import WORKSHEETS\UFH_Floors_BOQ_Updated.xlsx | Floors | Updated |
| MEASUREMENT UFHare\Draft Excel Bills before Import WORKSHEETS\Measurement Excel TEST Files\UFH_Demolitions_BOQ.xlsx | Demolitions | Complete |
| MEASUREMENT UFHare\Draft Excel Bills before Import WORKSHEETS\Measurement Excel TEST Files\UFH_Doors_Windows_Schedule.xlsx | Doors/Windows | Schedule |

#### Preliminaries

| File | Description |
| --- | --- |
| MEASUREMENT UFHare\Preliminaries\EXAMPLE Preliminaries Trade - UFHare Compliance.xlsx | Preliminaries framework |

### 3.8 Drawing Registers

| File | Description |
| --- | --- |
| Drawing Registers\A-(00)0000-DRAWING REGISTER(-).pdf | Master drawing register |
| Drawing Registers\A-(00)0001-TRANSMITTAL SLIP 2025-11-12-(-).pdf | Latest transmittal |

### 3.9 Templates

| File | Description |
| --- | --- |
| Templates\MORNING STAR Graaf-Reinet CURRENT TenderBills.xlsx | BOQ format template |

__________________________________________________

## 4. MEASUREMENT STATUS BY TRADE

| Trade | SSM7 Section | Status | Files | Notes |
| --- | --- | --- | --- | --- |
| Preliminaries | 1 | Framework | 1 | Template exists, needs customization |
| Demolitions | 2 | Complete | 3 | Multiple iterations, final version available |
| Alterations | 3 | Pending | 0 | Part of demolitions scope |
| Earthworks | 4 | Partial | 1 | Site clearance needed, foundations measured |
| Concrete/Formwork/Rebar | 7 | Complete | 4 | Foundations (700mm) finalized |
| Masonry | 10 | Complete | 1 | 112m² blockwork + 78m² drywall |
| Waterproofing | - | Complete | 1 | DPM 186m², ablutions 89m² |
| Roofing | - | Complete | 1 | UFH_Roofing_085_086.md - NEW roofing 285m² |
| Carpentry & Joinery | - | Complete | 1 | 18 doors, 2 gates, 2 joinery units, 291m skirtings |
| Ceilings | - | Complete | 1 | 275m² total (Ce.01:239 + Ce.02:36), 145m bulkheads |
| Floor Coverings | - | Complete | 1 | 380m² tiles, 220m skirtings, verified |
| Wall Finishes | - | Complete | 1 | 228m² plaster, 98m² tiles, 402m² paint |
| Glazing | - | Complete | 1 | 28 windows + 17 shopfronts = 80m² glass |
| Metalwork | - | Complete | 1 | 2 gates, 4 steel posts, 9 bollards |
| Plumbing | - | Complete | 1 | 20 fittings, 300m pipe, 60m drainage |
| Electrical | - | Package | 1 | ZIP package available |
| HVAC | - | Package | 1 | ZIP package available |
| Fire Protection | - | Package | 1 | ZIP package available |
| External Works | 22 | Complete | 1 | 128m² paving, 80m edging, see UFH_External_Works_190_195.md |
| Provisional Sums | 23 | Complete | 1 | R415k total PC sums + 5% contingency |

Overall Progress: ~85% complete (Phase 2 Measurement substantially complete)

__________________________________________________

## 5. OUTSTANDING QUERIES & ARCHITECT CLARIFICATIONS

### Resolved (from SVA Comments 2025-12-11)

| Q# | Query | Response | Measurement Action |
| --- | --- | --- | --- |
| 1 | External paving extent | Per A-(11)1000 to road edge | Bosun charcoal paver, bollards, R100k landscaping |
| 5 | Structural drawings | Received 10-12-2025 | Use Rev E drawings |
| 7 | Glass thickness | Cannot specify | Use PC sum for glazing |
| 11 | Cavity vs solid walls | Structural dwgs issued | Refer structural for wall types |
| 12 | Garage doors | None in project | Exclude from BOQ |
| 13 | Facade doors | Refer door schedules | Measure per details D01-D08 |
| 14 | Timber flooring removal | Refer A-(52)1001 | Await engineer on sub-structure |
| 15 | Floor tile removal | Refer floor finishes | Adhesive spec to follow |
| 17 | Steps and nib wall | Dimensions on plans | Scale from drawings |
| 18 | Fence | None required | PC Sum R50,000 |
| 19 | Roof areas | Pitch on sections | Measure on slope from sections |
| 20 | Ceiling demolition | All ceilings demolished | Full ceiling removal |
| 24 | Existing ablutions | Upgrade per A-(50)6001 | Measure upgrade work |
| 25 | Finishing schedule | Refer A-(51)1001 | Use wall finishes layout |
| 28 | Concrete beam finish | Class 1 accuracy | Note in descriptions |

### Outstanding - Awaiting Response

| Q# | Query | Responsible | Status |
| --- | --- | --- | --- |
| 4 | Civil dwgs, water/drain blanking | Civil Eng (Alex Semple) | PENDING |
| 6 | H&S Spec and BOQ | H&S Agent (Jay Bhana) | PENDING |
| 10 | Loadbearing walls, roof support | Struct Eng | PENDING |
| 21 | Drainage/water line retention | Civil Eng | PENDING |
| 22 | Electrical removal scope | Elec Eng | PENDING |
| 26 | Wall stability, temp support method | Struct Eng | PENDING |
| 27 | Demolition sequence required? | Struct Eng | PENDING |

### PC Sums Confirmed

Landscaping: R100,000

Fence allowance: R50,000

Glass (if unspecified): TBD

__________________________________________________

## 6. TASK LIST FOR BOQ COMPLETION

### PHASE 1: PRE-MEASUREMENT TASKS

#### Document Review & Preparation

[x] UFH-001: Review Query List Rev 2 responses (28 queries reviewed, 15 resolved, 7 pending)

[x] UFH-002: Extract Electrical BOQ from ZIP package (5 files extracted)

[x] UFH-003: Extract Fire Detection BOQ from ZIP package (3 files extracted)

[x] UFH-004: Extract HVAC package contents (3 files extracted)

[x] UFH-005: Extract Fire Protection package contents (3 files extracted)

[ ] UFH-006: Follow up on outstanding structural/civil query responses from Alex Semple

[ ] UFH-007: Follow up on HSE specification from Jay Bhana / Stiaan Burger

[ ] UFH-008: Review drawing register for any missing drawings

__________________________________________________

### PHASE 2: MEASUREMENT BY TRADE (SSM7 Order)

#### PRELIMINARIES (SSM7 Section 1)

[ ] UFH-010: Review existing Preliminaries framework file

[ ] UFH-011: Update contract data and employer requirements

[ ] UFH-012: Add site-specific requirements (access, working hours, restrictions)

[ ] UFH-013: Include temporary works requirements

[ ] UFH-014: Add health & safety requirements per H&S Spec

[ ] UFH-015: Finalize preliminaries pricing items

#### DEMOLITIONS (SSM7 Section 2)

[x] UFH-020: Measure demolition work from demolition plans (Complete - UFH_Demolitions_BOQ.xlsx)

[x] UFH-021: Verify demolition quantities against Rev 3 drawings (Drawing A-01-1002 Rev3 reviewed)

[ ] UFH-022: Include disposal arrangements in descriptions

[ ] UFH-023: Cross-check making good requirements with alterations

Demolition Scope (from A-01-1002 Rev3):

Built-in joinery & cupboards (with concrete soffits)

Fireplace, veranda (columns/walls/ceiling)

Facade doors/windows, garage walls/doors

Sanware with drainage blanking

Floor tiles, internal brick walls

All windows with ironmongery

Steps, nib wall, reception desk

ALL roof structures (garage, main, veranda)

ALL ceilings (per query response)

External wall with fence, gates

External paving, concrete slab

#### ALTERATIONS (SSM7 Section 3)

[ ] UFH-030: Review scope of alterations from drawings

[ ] UFH-031: Measure wall removals (m2)

[ ] UFH-032: Measure partition removals (m)

[ ] UFH-033: Measure door/window removals (No)

[ ] UFH-034: Measure sanitary fitting removals (No)

[ ] UFH-035: Include making good to wall ends and faces

#### EARTHWORKS (SSM7 Section 4)

[x] UFH-040: Calculate site clearance area (building footprint + 2m per DQRules) ~250m² estimated

[x] UFH-041: Measure bulk excavation for foundations (m3, 2m depth stages) 61m³ - see UFH_Bulk_Excavation_041.md

[x] UFH-042: Measure trench excavation (m3, 2m depth stages) Per foundation layout, 700mm depth

[x] UFH-043: Measure filling under floors (m3) 38m³ total (28m³ hardcore + 10m³ sand blinding) - see UFH_Filling_Under_Floors_043.md

[x] UFH-044: Include compaction requirements per structural spec 306m² total (186m² internal + 120m² external)

[x] UFH-045: Add keeping free of water item 1 Item + R15k P.Sum

[x] UFH-046: Measure external excavation for paving layerworks 29m³ excav, 18m³ G5 fill, 120m² bedding

Earthworks Estimates (from drawings):

Building footprint: ~186 m²

Site clearance: ~250 m² (footprint + 2m perimeter per DQRules)

Foundation depth: 700mm (<=2m stage)

Trench excavation: refer foundation layout for linear metres

External paving area: to be measured from A-(11)1000

#### CONCRETE, FORMWORK & REINFORCEMENT (SSM7 Section 7)

[x] UFH-050: Measure foundations (m3) 45m³ (107m × 0.6m × 0.7m) + 4m³ blinding

[x] UFH-051: Verify foundation measurements against Rev E drawings Verified - see UFH_Concrete_050_to_058.md

[x] UFH-052: Measure surface beds (m3) 24m³ (186m² × 0.125m)

[x] UFH-053: Measure ring beams (m3) 14m³ (RB1:11m³ + RB2:3m³)

[x] UFH-054: Measure formwork to foundations (m2) 150m²

[x] UFH-055: Measure formwork to ring beams (m2) 114m²

[x] UFH-056: Measure reinforcement from structural details (t) 6.0t estimated

[x] UFH-057: Measure concrete canopy per detail A-(53)2003 1m³ provisional

[x] UFH-058: Add test blocks item 60 No. cubes

#### PRECAST CONCRETE (SSM7 Section 8)

[x] UFH-060: Check drawings for any precast elements N/A - no precast in project

[x] UFH-061: Measure precast items if applicable (No or m) N/A

#### MASONRY (SSM7 Section 10)

[x] UFH-070: Measure blockwork walls (m2) from ground storey plan 112m² total

[x] UFH-071: Separate internal and external blockwork 36m² ext + 76m² int

[x] UFH-072: Measure blockwork to piers and pilasters (m) None identified

[x] UFH-073: Add fair face blockwork as extra over where required 36m² Platinum Satin

[x] UFH-074: Measure beam filling (m2) 22m²

[x] UFH-075: Measure closing cavities (m) N/A - solid walls

[x] UFH-076: Include DPC under walls 59m

[x] UFH-077: Add fabricated lintels (m) 36 No.

#### WATERPROOFING

[x] UFH-080: Check specifications for waterproofing requirements Reviewed

[x] UFH-081: Measure DPM under surface beds if required (m2) 186m²

[x] UFH-082: Measure waterproofing to ablutions (m2) 26m² floor + 63m² walls

#### ROOFING

[x] UFH-085: Review roof plan for any new roofing work Complete - NEW roofing (not repairs)

[x] UFH-086: Measure roofing work 285m² sheeting, 106m flashings, 44m gutters - see UFH_Roofing_085_086.md

#### CARPENTRY & JOINERY

[x] UFH-090: Measure timber door frames from door schedule (No) 18 No. frames

[x] UFH-091: Measure timber doors from door details D01-D08 (No) 18 doors + 2 gates

[x] UFH-092: Measure built-in joinery - Security Desk JT01 (No) 1 No. complete

[x] UFH-093: Measure built-in joinery - Kitchenette JT02 (No) 1 No. complete

[x] UFH-094: Measure skirtings from skirting drawing (m) 291m (Type 01: 197m, Type 02: 94m)

[x] UFH-095: Measure any other timber work from details Roof timber in P.Sum

#### CEILINGS

[x] UFH-100: Measure suspended ceilings from ceiling plan (m2) 275m² total

[x] UFH-101: Separate different ceiling types/heights Ce.01: 239m², Ce.02: 36m²

[x] UFH-102: Measure bulkheads and drops (m) 145m linear, 63m² soffits

[x] UFH-103: Include access panels (No) 7 No. 600x600 + 3 No. 450x450

[x] UFH-104: Add cornices/shadow lines (m) 266m shadow line

#### FLOOR COVERINGS

[x] UFH-110: Measure floor finishes from layout (Updated - UFH_Floors_BOQ_Updated.xlsx)

[x] UFH-111: Verify floor finishes quantities against Rev 1 drawing Verified: 350m² general + 30m² ablution

[x] UFH-112: Separate different floor finish types Fl.01, Fl.02, Fl.03 separated

[x] UFH-113: Measure skirtings by type (m) 220m total (Type 01: 95m, Type 02: 125m)

[x] UFH-114: Include floor preparation where required 380m² prep included

#### WALL FINISHES

[x] UFH-120: Measure plastering to walls (m2) 228m² (188 new + 40 patch)

[x] UFH-121: Measure plastering to columns/beams (m2) 45m² ring beams

[x] UFH-122: Measure wall tiling from wall finishes layout (m2) 98m² (96 WCs + 2 splashback)

[x] UFH-123: Measure paint to walls by type (m2) 402m² (WF01:266 + WF02:136)

[x] UFH-124: Measure paint to ceilings (m2) 114m² (bulkheads)

[x] UFH-125: No deductions for openings <=0.5m2 Applied - 106m² deducted

#### GLAZING

[x] UFH-130: Measure windows W01-W06 from detail drawings (No) 28 No. windows (W01-W06)

[x] UFH-131: Measure shopfronts SF01-SF09 from detail drawings (No) 17 No. shopfronts (SF01-SF09)

[x] UFH-132: Include glass types and specifications 80m² total glass area

[x] UFH-133: Include glazing beads and seals 265m perimeter seal

#### METALWORK

[x] UFH-140: Measure metal gates G01-G02 from detail drawings (No) 2 No. aluminium gates

[x] UFH-141: Measure any structural steelwork 4 No. RHS posts for shopfronts

[x] UFH-142: Measure handrails if applicable (m) None required

[x] UFH-143: Include bollards along road edge (No) 9 No. concrete bollards

#### PLUMBING & DRAINAGE

[x] UFH-150: Review ablution details for sanitary fittings 6 WC areas reviewed

[x] UFH-151: Measure sanitary fittings (No) 9 WC + 2 urinal + 8 WHB + 1 sink

[x] UFH-152: Measure pipework runs (m) 300m total (CW+HW+waste+vent)

[x] UFH-153: Include valves and accessories 25 valves + geyser + accessories

[x] UFH-154: Measure drainage connections 60m drainage + 3 IC + grease trap

#### ELECTRICAL INSTALLATION (Specialist Package)

[ ] UFH-160: Extract electrical BOQ from ZIP package

[ ] UFH-161: Review electrical scope and quantities

[ ] UFH-162: Integrate electrical BOQ into main document

[ ] UFH-163: Check for any provisional sums required

#### HVAC (Specialist Package)

[ ] UFH-170: Extract HVAC package from ZIP

[ ] UFH-171: Review HVAC BOQ (P8080M02-BOQ_RevA.xlsx)

[ ] UFH-172: Integrate HVAC BOQ into main document

[ ] UFH-173: Verify against HVAC layout drawing

#### FIRE PROTECTION (Specialist Package)

[ ] UFH-180: Extract fire protection package from ZIP

[ ] UFH-181: Review fire detection BOQ

[ ] UFH-182: Integrate fire protection into main document

#### EXTERNAL WORKS (SSM7 Section 22)

[x] UFH-190: Measure site clearance for paving area (m2) 150m²

[x] UFH-191: Measure excavation for paving layerworks (m3) 34m³

[x] UFH-192: Measure sub-base layers per civil drawing (m3) G5:19m³ + G7:4m³

[x] UFH-193: Measure paving - Bosun Smooth Ethnic Paver charcoal (m2) 128m² (104 light + 24 heavy)

[x] UFH-194: Measure paving edging/kerbs (m) 80m

[x] UFH-195: Measure concrete bollards (No) 9 No. (in Metalwork)

#### PROVISIONAL SUMS & PC ITEMS (SSM7 Section 23)

[x] UFH-200: Add Landscaping PC Sum - R100,000.00 Confirmed

[x] UFH-201: Review need for other provisional sums R415k total: Landscape R100k, Fence R50k, Glazing R50k, Roof R150k, Dewater R15k, Daywork R50k

[x] UFH-202: Add contingencies if required 5% recommended - TBD on final value

__________________________________________________

### PHASE 3: INTEGRATION & QA

#### Consolidation

[ ] UFH-210: Consolidate all trade measurements into single BOQ

[ ] UFH-211: Integrate specialist packages (Electrical, HVAC, Fire)

[ ] UFH-212: Add H&S BOQ items

[ ] UFH-213: Verify all items have descriptions per DQRules

[ ] UFH-214: Check units of measurement (m, m2, m3, No, t, kg)

#### Quality Assurance

[ ] UFH-220: Cross-check quantities against drawings

[ ] UFH-221: Verify measurement rules applied correctly per DQRules

[ ] UFH-222: Check for duplicate items

[ ] UFH-223: Verify no deduction rules applied correctly

[ ] UFH-224: Review deemed-to-include items

#### Review

[ ] UFH-230: Internal QS review of complete BOQ

[ ] UFH-231: Check item numbering sequence

[ ] UFH-232: Verify trade order per SSM7

[ ] UFH-233: Spell check and formatting review

__________________________________________________

### PHASE 4: FINAL ASSEMBLY

#### Formatting

[ ] UFH-300: Format BOQ for conventional presentation

[ ] UFH-301: Prepare QSPlus import version

[ ] UFH-302: Add cover page and contents

[ ] UFH-303: Add drawing list reference

[ ] UFH-304: Include preambles for each trade

#### Documentation

[ ] UFH-310: Prepare measurement notes/take-off summary

[ ] UFH-311: Document any assumptions made

[ ] UFH-312: List outstanding items requiring clarification

#### Submission

[ ] UFH-320: Final review before issue

[ ] UFH-321: Export PDF version

[ ] UFH-322: Issue draft BOQ for consultant review

[ ] UFH-323: Address review comments

__________________________________________________

## 7. SESSION LOG

Track work completed in each session for continuity:

| Session | Date | Tasks Completed | Next Task |
| --- | --- | --- | --- |
| 1 | 2026-01-04 | PROJECT_STATUS.md created. 78 tasks defined. Document inventory complete. | UFH-001 |
| 1 | 2026-01-04 | UFH-002,003,004,005 complete. Specialist packages extracted: Elec(5), FD(3), HVAC(3), Fire(3). | UFH-001 |
| 1 | 2026-01-04 | UFH-001 complete. Query list reviewed: 15 resolved, 7 pending. PC sums: R100k landscape, R50k fence. | UFH-006 |
| 1 | 2026-01-04 | Phase 2 started. Drawings reviewed: Foundation (S-01 Rev E), Demolition (A-01 Rev3), Ground Plan (A-11 Rev4). Building ~186m². | UFH-040 |
| 2 | 2026-01-04 | UFH-041 complete. Bulk excavation measured: 61m³ (186m² × 0.325m depth). Surface bed layerworks: 125mm slab + 50mm blinding + 150mm hardcore = 325mm. | UFH-043 |
| 2 | 2026-01-04 | UFH-043 complete. Filling under floors: 28m³ hardcore (150mm) + 10m³ sand blinding (50mm) = 38m³ total. | UFH-044 |
| 2 | 2026-01-04 | UFH-044,045,046 complete. Earthworks section finished. Compaction 306m², dewatering P.Sum R15k, external paving excavation 29m³. Total excavation 135m³. | UFH-050 |
| 2 | 2026-01-04 | UFH-050-058 complete. Concrete section finished. Total concrete 88m³ (Found 45, RB 14, SB 24, Canopy 1, Blinding 4). Formwork 272m². Rebar 6t. | UFH-060 |
| 2 | 2026-01-04 | UFH-060-082 complete. Precast N/A. Masonry 112m² blockwork + 78m² drywall. Waterproofing: DPM 186m², ablutions 89m². | UFH-085 |
| 3 | 2026-01-04 | UFH-085-086 complete. Roofing: NEW work (not repairs). 285m² Klip-Lok sheeting, 106m flashings, 44m gutters, 38m² waterproofing. P.Sum R150k roof structure. | UFH-090 |
| 3 | 2026-01-04 | UFH-090-095 complete. Carpentry & Joinery: 18 doors + 2 gates, JT01 Security Desk, JT02 Kitchenette, 291m skirtings. See UFH_Carpentry_Joinery_090_095.md | UFH-100 |
| 4 | 2026-01-04 | UFH-100-104 complete. Ceilings: Ce.01 239m² + Ce.02 36m² = 275m² total. Bulkheads 145m + 63m² soffits. 10 access panels. 266m shadow line. See UFH_Ceilings_100_104.md | UFH-111 |
| 4 | 2026-01-04 | UFH-111-114 verified (floors BOQ complete). UFH-120-125 complete. Wall Finishes: 228m² plaster, 98m² tiles, 402m² paint. See UFH_Wall_Finishes_120_125.md | UFH-130 |
| 4 | 2026-01-04 | UFH-130-133 complete. Glazing: 28 windows + 17 shopfronts = 80m² glass. See UFH_Glazing_130_133.md | UFH-140 |
| 4 | 2026-01-04 | UFH-140-143 complete. Metalwork: 2 gates, 4 steel posts, 9 bollards. See UFH_Metalwork_140_143.md | UFH-150 |
| 4 | 2026-01-04 | UFH-150-154 complete. Plumbing: 20 fittings, 300m pipework, 60m drainage. See UFH_Plumbing_150_154.md | UFH-190 |
| 4 | 2026-01-04 | UFH-190-195 complete. External Works: 128m² paving, 80m edging. UFH-200-202 complete. PC Sums R415k. See files. | Phase 3 |
| 5 | 2026-01-04 | UFH-210 complete. Created UFH_CONSOLIDATED_BOQ_DRAFT.md with all 14 trade measurements. See file for full BOQ structure. | UFH-211 |
| 5 | 2026-01-04 | UFH-213, UFH-214 complete. Created UFH_DQRules_Verification.md - all items COMPLIANT. Descriptions verified, units correct. | UFH-211 |

__________________________________________________

## 8. NOTES & ASSUMPTIONS

### Key Assumptions

Foundation depth is 700mm as per Claude measurements filename

Structural drawings at Rev E are current (highest revision)

Architectural drawings at Rev 4 are current for main plans

Specialist packages (Elec, HVAC, Fire) are complete and ready for integration

No basement or multi-storey work - ground floor conversion only

### Building Areas (from A-11-1000 Rev 4)

| Room | Area (m²) |
| --- | --- |
| Open Plan Offices | ~57 |
| Offices 3-5 | 41 |
| Strong Rooms 1-2 | 26 |
| Kitchenette | 9 |
| Passage | 24 |
| WCs (4 total) | 11 |
| Student Areas | 18 |
| Approx Total | ~186 m² |

### Wall Types

Ma.01: Existing Brickwork (retain/alter)

Ma.02: New Brickwork (measure)

Ma.03: Drywalled - Gyproc (measure)

Ma.04: Reinforced Concrete (per structural)

### Architect Instructions (from Query List responses)

Paving to extend to road edge per A-(11)1000

Paving specification: Bosun Smooth Ethnic Paver (Charcoal)

Include concrete bollards along road edge

Landscaping PC Sum: R100,000

Fence PC Sum: R50,000 (no fence construction)

No garage doors in project

All ceilings to be demolished

Existing ablutions to be upgraded (not demolished)

Concrete beam finish: Class 1 accuracy

Glass thickness: use PC sum (architect cannot specify)

### Reference Documents

ASAQS Standard System of Measuring Building Work, Seventh Edition (2015)

DQRules v2.0 - Dell Quantity Surveying AI Measurement Rules

ASAQS Model Bills of Quantities with Rules

### Split PDF Files Available

Large PDFs have been pre-split and are available in Projects\UFHARE\split_pdfs\. See split_pdfs\split_manifest.md for full index.

Manifest Info: Processed 2026-01-04, 28 PDFs processed, 130+ output files total.

Summary of Split Files:

| Original | Size | Pages | Method | Output Files |
| --- | --- | --- | --- | --- |
| A-(01)1002-Demolition Plan(3).pdf | 1.6MB | 1 | render | 1 PNG (1.7MB) |
| A-(11)1000-Ground Storey Plan-(4).pdf | 2.1MB | 1 | render | 1 PNG (2.9MB) |
| A-(11)1001-Roof Plan-(4).pdf | 1.4MB | 1 | render | 1 PNG (1.7MB) |
| A-(11)1003-General Arrangement Layout-(4).pdf | 1.9MB | 1 | render | 1 PNG (1.9MB) |
| A-(12)2000-Sections-(4).pdf | 5.4MB | 1 | render | 1 PNG (4.2MB) |
| A-(13)3000-Elevations-(4).pdf | 11.3MB | 1 | render | 1 PNG (5.2MB) |
| A-(14)1000-Ceiling Plan-(3).pdf | 1.3MB | 1 | render | 1 PNG (1.7MB) |
| A-(14)1003-GROUND STOREY CEILING PLAN (1).pdf | 1.3MB | 1 | render | 1 PNG (1.8MB) |
| A-(50)6001-Ablution Details-(1).pdf | 1.4MB | 1 | render | 1 PNG (1.2MB) |
| A-(52)1001-Floor Finishes Layout(1).pdf | 1.5MB | 1 | render | 1 PNG (2.1MB) |
| A-(52)1002-Skirtings(1).pdf | 1.4MB | 1 | render | 1 PNG (1.7MB) |
| A-(53)2001-Seating and Duct Detail-(1).pdf | 1.3MB | 1 | render | 1 PNG (0.8MB) |
| A-(74)1001-Fixed Furniture and Fittings Key Plan(1).pdf | 1.6MB | 1 | render | 1 PNG (0.9MB) |
| New Paving Layout.pdf | 3.3MB | 1 | render | 1 PNG (3.2MB) |
| P8099E01-001_C - POWER LAYOUT.pdf | 1.4MB | 1 | render | 1 PNG (1.8MB) |
| P8099E01-002_C - LIGHTINGLAYOUT.pdf | 1.3MB | 1 | render | 1 PNG (1.5MB) |
| P8080M07-001_A - FIRE AND WAYFINDING LAYOUT.pdf | 1.9MB | 1 | render | 1 PNG (1.7MB) |
| S-01-25055-20-001-Rev E-Foundation Layout.pdf | 5.3MB | 1 | render | 1 PNG (5.5MB) |
| S-01-25055-20-001-Rev E-Foundation Layout- Ron Marked.pdf | 5.9MB | 1 | render | 1 PNG (5.6MB) |
| S-01-25055-20-002-Rev E-Surface Bed Layout.pdf | 4.6MB | 1 | render | 1 PNG (4.2MB) |
| S-01-25055-20-003-Rev E-Ring Beam Layout.pdf | 4.2MB | 1 | render | 1 PNG (3.6MB) |
| S-01-25055-20-004-Rev D-Sections.pdf | 3.3MB | 1 | render | 1 PNG (3.5MB) |
| UHF Alice Campus Finance Office - Electrical Spec Rev00 (251212-P8080).pdf | 3.2MB | 40 | render | 40 PNGs (71KB-1.8MB each) |
| UFH Alice Campus Finance Office - Fire Detection Spec Rev00 (251212-P8080).pdf | 2.4MB | 42 | render | 42 PNGs (33KB-656KB each) |

### Handling Large PDF Files

When reading large PDF files (typically >500KB), you may encounter HTTP 413 (Request Too Large) errors. Use the PDF Splitter Module to handle these:

Reference Files:

Reference\PDF_Splitter_Module.py - Python module with split functions

Reference\PDF_Splitter_Guide.md - Usage documentation

Quick Usage:

from Reference.PDF_Splitter_Module import handle_large_pdf, cleanup_split_files

# Smart handler - automatically chooses best strategy
result = handle_large_pdf("path/to/large_drawing.pdf")

if result.success:
    for part_file in result.split_files:
        # Read and process each part
        pass
    cleanup_split_files(result)  # Optional: cleanup temp files

Command Line:

python Reference/PDF_Splitter_Module.py "Projects/path/to/large.pdf" 500

Strategy:

Multi-page PDFs → Split into smaller PDFs

Single-page large PDFs → Render to image (PNG/JPG)

Files under 500KB → Return original (no split needed)

__________________________________________________

Document created: 2026-01-04

Next review: Upon session restart